## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-09-03 | Done | Max 4 hours tasks | Kickoff | Meeting |  | 1 | 1 | 0
2024-09-03 | Done | Max 4 hours tasks | Stakeholder presentation | Meeting |  | 2 | 2 | 0
2024-09-03 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-09-03 | Done | Max 4 hours tasks | More information about this year | Meeting |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-04 | Done | Max 4 hours tasks | Podcast: Former Netflix CEO | Study |  | 2 | 2.5 | 0.5 | https://adsai.buas.nl/Study%20Content/Leadership%20And%20Success/UnlockingEntrepreneurialSuccess.html
2024-09-04 | Done | Max 4 hours tasks | Ted Talk: Respectful to coworkers | Study |  | 0.5 | 0.5 | 0 | https://adsai.buas.nl/Study%20Content/Leadership%20And%20Success/ShapingYourSuccessandImpact.html
2024-09-04 | Done | Max 4 hours tasks | Conway’s Law | Study |  | 1 | 0.5 | -0.5 | https://adsai.buas.nl/Study%20Content/Leadership%20And%20Success/Conway'sLaw.html
2024-09-04 | Done | Max 4 hours tasks | Machine Learning System Design | Study |  | 1 | 0 | -1 | https://adsai.buas.nl/Study%20Content/System%20Design/
2024-09-04 | Done | Max 4 hours tasks | Business Requirement Document (BRD) | Study |  | 1 | 1.5 | 0.5 | https://uit.stanford.edu/pmo/business-requirements-doc
2024-09-04 | Cancelled | Max 4 hours tasks | Apache Spark Module 0 |  |  | 2 | 0 | -2 | https://adsai.buas.nl/Study%20Content/Apache%20Spark/README.html
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-05 | Done | Max 4 hours tasks | Standup | Meeting |  | 0.5 | 0.5 | 0
2024-09-05 | Done | Max 4 hours tasks | team building | Meeting |  | 0.5 | 0.5 | 0
2024-09-05 | Done | Max 4 hours tasks | Stakeholder lectures | Study |  | 2 | 2 | 0
2024-09-05 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-09-05 | Done | Max 4 hours tasks | Read into the esports project |  |  | 2 | 1 | -1
2024-09-05 | Done | Max 4 hours tasks | planning things ahead for the project |  |  | 2 | 3 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-06 | Done | Max 4 hours tasks | Machine Learning System Design | Study |  | 2 | 3 | 1
2024-09-06 | Cancelled | Max 4 hours tasks | Apache Spark Module 0 | Study |  | 2 | 0 | -2
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 25.5 | 22 | -3.5
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2024-09-09 | Done | Max 4 hours tasks | Break | Meeting |  | 1 | 1 | 0
2024-09-09 | Done | Max 4 hours tasks | Lecture from William | Lecture |  | 3 | 3 | 0
2024-09-09 | Done | Max 4 hours tasks | Research esports | Study |  | 1 | 1 | 0
2024-09-09 | Done | Max 4 hours tasks | Test some of the code/devices | Study |  | 3 | 3 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-10 | Done | Max 4 hours tasks | Official kickoff at the Hive | Lecture |  | 1 | 1 | 0
2024-09-10 | Done | Max 4 hours tasks | Lecture by Paris and Kiana | Lecture |  | 2 | 2 | 0
2024-09-10 | Done | Max 4 hours tasks | Q&A | Meeting |  | 1 | 1 | 0
2024-09-10 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-11 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.25 | 0.25 | 0
2024-09-11 | Done | Max 4 hours tasks | Read the book | Study |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-12 | Done | Max 4 hours tasks | Research into what coaches do | Research |  | 2 | 2 | 0
2024-09-12 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-09-12 | Done | Max 4 hours tasks | Make presentation with all notable ways to improve | Research |  | 2 | 3 | 1
2024-09-12 | Done | Max 4 hours tasks | Meeting with Bram | Meeting |  | 0.5 | 0.5 | 0
2024-09-12 | Done | Max 4 hours tasks | Testing out devices in the hive | Programming |  | 1.5 | 1.5 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-13 | Done | Max 4 hours tasks | Meeting with Team | Meeting |  | 0.5 | 0.5 | 0
2024-09-13 | Done | Max 4 hours tasks | Reading the book | Research |  | 1 | 1 | 0
2024-09-13 | Done | Max 4 hours tasks | Worklog/learninglog | Evidencing |  | 0.5 | 1 | 0.5
|  |  |  | Total Hours |  | 23.25 | 24.75 | 1.5
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-09-16 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-09-16 | Done | Max 4 hours tasks | Learning log/ Worklog | Evidencing |  | 0.5 | 1 | 0.5
2024-09-16 | Done | Max 4 hours tasks | Standup | Meeting |  | 0.5 | 0.5 | 0
2024-09-16 | Done | Max 4 hours tasks | Problem Analysis workshop by William | Meeting |  | 2 | 2 | 0
2024-09-17 | Done | Max 4 hours tasks | Trello board | Meeting |  | 1 | 1 | 0
2024-09-18 | Done | Max 4 hours tasks | emails for presentation draft | Study |  | 0.5 | 0.5 | 0
2024-09-19 | Done | Max 4 hours tasks | Presentation prep | Study |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-17 | Done | Max 4 hours tasks | visuals for OBS | Study |  | 2 | 3 | 1
2024-09-18 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.25 | 0.25 | 0
2024-09-19 | Done | Max 4 hours tasks | emails for presentation draft | Study |  |  |  | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-18 | Done | Max 4 hours tasks | Meeting with team | Study |  | 0.25 | 0.25 | 0
2024-09-19 | Done | Max 4 hours tasks | sending out emails for the presentation | Meeting |  | 1 | 1 | 0
2024-09-20 | Done | Max 4 hours tasks | More feedback from Bram | Meeting |  | 0.5 | 0.5 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-19 | Done | Max 4 hours tasks | Helping others with testing | Programming |  | 2 | 2 | 0
2024-09-20 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-09-21 | Done | Max 4 hours tasks | Presentation prep | Study |  | 3 | 4 | 1
2024-09-22 | Done | Max 4 hours tasks | Worklog/learninglog | Evidencing |  | 1.5 | 1 | -0.5
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-20 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.25 | 0.25 | 0
2024-09-21 | Done | Max 4 hours tasks | Making presentation | Meeting |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 19.25 | 23.25 | 4
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-09-23 | Done | Max 4 hours tasks | Business understanding presentation | Lecture |  | 1.5 | 2 | 0.5
| Done | Max 4 hours tasks | Kanban workshop | Lecture |  | 1 | 1
| Done | Max 4 hours tasks | break | Break |  | 1 | 1
| Done | Max 4 hours tasks | Meetings with Bram/Samuel | Meeting |  | 0.5 | 1
| Done | Max 4 hours tasks | Recording footage for data | Study |  | 1 | 1.5
| Done | Max 4 hours tasks | Data management plan | Research |  | 1 | 1
Max 4 hours tasks
2024-09-24 | Done | Max 4 hours tasks | meeting with team | Meeting |  | 0.25 | 0.25 | 0
| Delayed | Max 4 hours tasks | questions for interviews | Research |  | 1 | 0 | -1
| In-Progress | Max 4 hours tasks | Data management plan | Research |  | 0.5 | 0.5 | 0
| Done | Max 4 hours tasks | Trello | Evidencing |  | 1 | 1 | 0
| Done | Max 4 hours tasks | Worklog/learninglog | Evidencing |  | 1 | 1.5
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-25 | Done | Max 4 hours tasks | meeting with team | Meeting |  | 0.5 | 0.5 | 0
| Done | Max 4 hours tasks | questions for interviews | Research |  | 1 | 2 | 1
| Done | Max 4 hours tasks | Riot API | Research |  | 0.5 | 0.5 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-26 | Done | Max 4 hours tasks | Riot API | Research |  | 1 | 1 | 0
| In-Progress | Max 4 hours tasks | Data management plan | Research |  | 0.5 | 2 | 1.5
| Done | Max 4 hours tasks | Sportday | Break |  | 4 | 4 | 0
| Done | Max 4 hours tasks | Break | Break |  | 1 | 1.5 | 0.5
|  | Max 4 hours tasks | [5 empty] | 0
2024-09-27 | Done | Max 4 hours tasks | meeting with team | Meeting |  | 0.5 | 0.5 | 0
| Cancelled | Max 4 hours tasks | Interview | Meeting |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 19.75 | 23.75 | 4
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
31/9/24 | Done | Max 4 hours tasks | Feedback from bram |  |  | 0.5 | 0.5 | 0
31/9/24 | Done | Max 4 hours tasks | Learning log/ Worklog |  |  | 2 | 2 | 0
31/9/24 | Done | Max 4 hours tasks | Break |  |  | 1 | 1 | 0
31/9/24 | Done | Max 4 hours tasks | Revise learning log from feedback |  |  | 0.5 | 0.5 | 0
31/9/24 | Done | Max 4 hours tasks | Look into KPIs |  |  | 1 | 2 | 1
31/9/24 | Done | Max 4 hours tasks | DMP |  |  | 1 | 0.5 | -0.5
31/9/24 | Done | Max 4 hours tasks | Interview questions |  |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-01 | Done | Max 4 hours tasks | teammeeting | Meeting |  | 0.5 | 0.5 | 0
2024-10-01 | Done | Max 4 hours tasks | Look into KPIs | Study |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-02 | Done | Max 4 hours tasks | teammeeting | Meeting |  | 1 | 1 | 0
2024-10-02 | Done | Max 4 hours tasks | Feedback on questions | Debugging |  | 0.5 | 0.5 | 0
2024-10-02 | Done | Max 4 hours tasks | KPI research | Research |  | 1 | 0.5 | -0.5
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-03 | Done | Max 4 hours tasks | Meeting | Meeting |  | 1 | 1 | 0
2024-10-03 | Done | Max 4 hours tasks | questions for interviews | Meeting |  | 1 | 1 | 0
2024-10-03 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1.5 | 0.5
2024-10-03 | Done | Max 4 hours tasks | Presentation from Game group | Meeting |  | 1 | 1 | 0
2024-10-03 | Done | Max 4 hours tasks | Looked into what stats to use for the dashboard rating |  |  | 2 | 2 | 0
2024-10-03 | Done | Max 4 hours tasks | DMP |  |  | 0.5 | 0.5 | 0
2024-10-03 | Done | Max 4 hours tasks | Emails/messages |  |  | 0.5 | 1 | 0.5
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-04 | Done | Max 4 hours tasks | Teammeeting | Meeting |  | 0.5 | 0.5 | 0
2024-10-04 | Done | Max 4 hours tasks | Finished the DMP | Evidencing |  | 2 | 2 | 0
2024-10-04 | Done | Max 4 hours tasks | Revised the question from Bram's Feedback | Debugging |  | 0.5 | 1 | 0.5
2024-10-04 | Done | Max 4 hours tasks | Trello | Evidencing |  | 0.5 | 0.5 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 22.5 | 24 | 1.5
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-10-07 | Done | Max 4 hours tasks | Interview with Head Coach Itopito | Meeting |  | 1 | 2 | 1
2024-10-07 | Done | Max 4 hours tasks | OBS | Research |  | 2 | 3 | 1
2024-10-07 | Done | Max 4 hours tasks | Riot API | Research |  | 1 | 1 | 0
2024-10-07 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-10-07 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-08 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-09 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 1 | 1 | 0
2024-10-09 | Delayed | Max 4 hours tasks | Interview with Coach Siko esports | Meeting |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-10 | Done | Max 4 hours tasks | Interview Fian, League coach | Meeting |  | 2 | 2 | 0
2024-10-10 | Done | Max 4 hours tasks | prep for interview | Research |  | 2 | 2 | 0
2024-10-10 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-10-10 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 1 | 2 | 1
2024-10-10 | Done | Max 4 hours tasks | Gather all information from interviews | Study |  | 1 | 0.5 | -0.5
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-11 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 1 | 1 | 0
2024-10-11 | Delayed | Max 4 hours tasks | Data understanding | Research |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 18 | 22.5 | 4.5
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-10-14 | Done | Max 4 hours tasks | Meeting with team |  |  | 1 | 1 | 0
2024-10-14 | Cancelled | Max 4 hours tasks | Interview with old ex assistant coach Juv3nile |  |  | 1 | 2 | 1
2024-10-14 | Planned | Max 4 hours tasks | Feedback sesh |  |  | 0.5 | 0.5 | 0
2024-10-14 | Done | Max 4 hours tasks | break |  |  | 1 | 1 | 0
2024-10-14 | Delayed | Max 4 hours tasks | OBS |  |  | 0 | 0 | 0
2024-10-14 | Delayed | Max 4 hours tasks | documentation |  |  | 0 | 0 | 0
2024-10-14 | Done | Max 4 hours tasks | Data Business understanding |  |  | 1 | 2 | 1
2024-10-14 | Done | Max 4 hours tasks | Learning log/ Worklog |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-15 | Done | Max 4 hours tasks | Teammeeting |  |  | 0.5 | 0.5 | 0
2024-10-15 | Delayed | Max 4 hours tasks | Flowchart |  |  | 1 | 0 | -1
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-16 | Done | Max 4 hours tasks | Teammeeting |  |  | 0.5 | 0.5 | 0
2024-10-16 | Done | Max 4 hours tasks | Researching best quality/storage size for OBS recordings |  |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-17 | Done | Max 4 hours tasks | Finished OBS settings for pcs in the Hive |  |  | 1 | 2 | 1
2024-10-17 | Done | Max 4 hours tasks | Feedback with bram |  |  | 0.5 | 0.5 | 0
2024-10-17 | Done | Max 4 hours tasks | Working on presentation |  |  | 3 | 4 | 1
2024-10-17 | Done | Max 4 hours tasks | Ideas for dashboard |  |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-18 | Done | Max 4 hours tasks | Standup |  |  | 0.5 | 0.5 | 0
2024-10-18 | Done | Max 4 hours tasks | Working learning log |  |  | 1 | 1 | 0
2024-10-18 | Done | Max 4 hours tasks | sending out emails for the presentation |  |  | 1 | 1 | 0
2024-10-18 | In-Progress | Max 4 hours tasks | Virtual cameras |  |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-02-22 | Done | Max 4 hours tasks | Interview with Assistant Coach Milan |  |  | 1.5 | 2 | 0.5
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 19 | 25.5 | 6.5
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-10-28 | Done | Max 4 hours tasks | Research into KPIs |  |  | 1 | 2 | 1
2024-10-28 | Done | Max 4 hours tasks | Trello meeting |  |  | 0.5 | 0.5 | 0
2024-10-28 | Done | Max 4 hours tasks | break |  |  | 1 | 1 | 0
2024-10-28 | Done | Max 4 hours tasks | getting footage for eyetracker/emotion |  |  | 1 | 2 | 1
2024-10-28 | Done | Max 4 hours tasks | presentation prep |  |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-29 | Done | Max 4 hours tasks | sending out emails for the presentation |  |  | 0.5 | 1 | 0.5
2024-10-29 | Done | Max 4 hours tasks | meeting |  |  | 0.5 |  | -0.5
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-30 | Done | Max 4 hours tasks | meeting |  |  | 0.5 | 0.5 | 0
2024-10-30 | Done | Max 4 hours tasks | learning log |  |  | 1 | 1 | 0
2024-10-30 | Done | Max 4 hours tasks | preperation for presentation |  |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-10-31 | Done | Max 4 hours tasks | meeting with Oscar |  |  | 0.5 | 1 | 0.5
2024-10-31 | Done | Max 4 hours tasks | meeting with team |  |  | 1 | 1 | 0
2024-10-31 | Done | Max 4 hours tasks | checking missing pieces of presenation |  |  | 2 | 2 | 0
2024-10-31 | Done | Max 4 hours tasks | Setting up presentation |  |  | 2 | 2 | 0
2024-10-31 | Done | Max 4 hours tasks | Presentation |  |  | 1 | 3 | 2
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-01 | Done | Max 4 hours tasks | meeting with team |  |  | 0.5 | 0.5 | 0
2024-11-01 | Done | Max 4 hours tasks | looking into feedback from presentation |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 18 | 22.5 | 4.5
Week 9
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-11-04 | Done | Max 4 hours tasks | gathering files for Bram |  |  | 1 | 1 | 0
2024-11-04 | Done | Max 4 hours tasks | break |  |  | 1 | 1 | 0
2024-11-04 | Done | Max 4 hours tasks | trello meeting |  |  | 0.5 | 0.5 | 0
2024-11-04 | Done | Max 4 hours tasks | Helping with live eye tracker |  |  | 2 | 5 | 3
2024-11-04 | Done | Max 4 hours tasks | Setting up PCs upstairs |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-05 | Done | Max 4 hours tasks | Ethics from oscar |  |  | 0.5 | 1 | 0.5
2024-11-05 | Done | Max 4 hours tasks | Meeting with team |  |  | 0.5 | 0.5 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-06 | Done | Max 4 hours tasks | Meeting with team |  |  | 0.5 | 0.5 | 0
2024-11-06 | Done | Max 4 hours tasks | Learning log/ Worklog |  |  | 1 | 3 | 2
2024-11-06 | Done | Max 4 hours tasks | Ethics from oscar |  |  | 0.5 | 0.5 | 0
2024-11-06 | Done | Max 4 hours tasks | DMP |  |  | 0.5 | 0.5 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-07 | Done | Max 4 hours tasks | break |  |  | 1 | 1 | 0
2024-11-07 | Done | Max 4 hours tasks | trello meeting |  |  | 0.5 | 1 | 0.5
2024-11-07 | Done | Max 4 hours tasks | feedback sessions |  |  | 0.5 | 0.5 | 0
2024-11-07 | Done | Max 4 hours tasks | vritual cam? |  |  | 2 | 2 | 0
2024-11-07 | Delayed | Max 4 hours tasks | DMP? |  |  | 1 | 0 | -1
2024-11-07 | Done | Max 4 hours tasks | Learning log/ Worklog? |  |  | 1 | 2 | 1
2024-11-07 | Done | Max 4 hours tasks | Helping with debugging | Debugging |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-08 | Done | Max 4 hours tasks | Looking into Bram's feedback content | Study |  | 2 | 3 | 1
2024-11-08 | Done | Max 4 hours tasks | Teammeeting | Meeting |  | 0.5 | 0.5 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 19.5 | 26.5 | 7
Week 10
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-11-11 | Done | Max 4 hours tasks | Trello meeting | Meeting |  | 0.5 | 1 | 0.5
2024-11-11 | Done | Max 4 hours tasks | break | Break |  | 1 | 1 | 0
2024-11-11 | Done | Max 4 hours tasks | Looking into Bram's feedback content | Study |  | 2 | 2 | 0
2024-11-11 | Done | Max 4 hours tasks | testing the setups in the Hive | Testing |  | 3 | 4 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-12 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.5 | 0.5 | 0
2024-11-12 | Done | Max 4 hours tasks | Looking into Gido's content | Study |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-13 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.5 | 0.5 | 0
2024-11-13 | Done | Max 4 hours tasks | Reviewing KPIs | Research |  |  |  | 0
2024-11-13 | Done | Max 4 hours tasks | Watching back Interviews | Research |  |  |  | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-14 | Done | Max 4 hours tasks | feedback from presentation | Research |  | 2 | 2 | 0
2024-11-14 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-11-14 | Done | Max 4 hours tasks | setup testing | Testing |  | 4 | 4 | 0
2024-11-14 | Done | Max 4 hours tasks | trello meeting | Meeting |  | 1 | 1 | 0
| Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.5 | 0.5 | 0
2024-11-15 | Done | Max 4 hours tasks | RoI discussion | Meeting |  | 2 | 3 | 1
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 20 | 22.5 | 2.5
Week 11
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-11-18 | Done | Max 4 hours tasks | ILO checking | Research |  | 1 | 2 | 1
2024-11-18 | Done | Max 4 hours tasks | DMP and Fair update | Debugging |  | 1 | 1 | 0
2024-11-18 | Done | Max 4 hours tasks | break | Break |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-19 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.5 | 0.5 | 0
2024-11-19 | Done | Max 4 hours tasks | ILOs | Study |  | 2 | 2 | 0
2024-11-19 | Done | Max 4 hours tasks | RoI discussion | Meeting |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-20 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.5 | 0.5 | 0
2024-11-20 | Done | Max 4 hours tasks | Peer reviews | Evidencing |  | 2 | 1 | -1
2024-11-20 | Done | Max 4 hours tasks | Worklog/learninglog | Evidencing |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
| Cancelled | Max 4 hours tasks | ILO meeting | Meeting |  |  |  | 0
| Cancelled | Max 4 hours tasks | feedback sessions | Meeting |  | 0.5 | 0.5 | 0
2024-11-21 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2024-11-21 | Done | Max 4 hours tasks | Discussion modeling | Meeting |  | 1 | 1 | 0
2024-11-21 | Done | Max 4 hours tasks | Chess | Break |  | 0.5 | 0.5 | 0
2024-11-21 | Done | Max 4 hours tasks | ILOs | Evidencing |  | 1 | 1 | 0
2024-11-21 | Done | Max 4 hours tasks | Testing PCs upstairs | Debugging |  | 2 | 4 | 2
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-22 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.5 | 0.5 | 0
2024-11-22 | Done | Max 4 hours tasks | Looking into next semester | Research |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 18.5 | 20.5 | 2
Week 12
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2024-11-25 | Done | Max 4 hours tasks | feedback sessions | Meeting |  | 0.5 | 0.5 | 0
2024-11-25 | Done | Max 4 hours tasks | Meeting with team | Meeting |  | 0.5 | 0.5 | 0
2024-11-25 | Done | Max 4 hours tasks | break | Break |  | 1 | 2 | 1
2024-11-25 | Done | Max 4 hours tasks | Worklog/learninglog | Evidencing |  | 1 | 1 | 0
2024-11-25 | Done | Max 4 hours tasks | Adding to trello | Planning |  | 1 | 1 | 0
2024-11-25 | Done | Max 4 hours tasks | gathering documents for evidence | Evidencing |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-26 | Done | Max 4 hours tasks | teammeeting | Meeting |  | 0.5 | 0.5 | 0
2024-11-26 | Done | Max 4 hours tasks | ethics review | Study |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-27 | Done | Max 4 hours tasks | teammeeting | Meeting |  | 0.5 | 0.5 | 0
2024-11-27 | Done | Max 4 hours tasks | qualitive analysis: presentation | Research |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-28 | Done | Max 4 hours tasks | Trello | Meeting |  | 0.5 | 1 | 0.5
2024-11-28 | Done | Max 4 hours tasks | Looking into ILOs | Evidencing |  | 1 | 1 | 0
2024-11-28 | Done | Max 4 hours tasks | Testing PCs upstairs | Debugging |  | 2 | 3 | 1
2024-11-28 | Done | Max 4 hours tasks | Chess | Break |  | 1 | 1 | 0
2024-11-28 | Done | Max 4 hours tasks | break | Break |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-11-29 | Done | Max 4 hours tasks | teammeeting |  |  | 0.5 | 0.5 | 0
2024-11-29 | Cancelled | Max 4 hours tasks | BRD |  |  | 1 | 0 | -1
2024-11-29 | Done | Max 4 hours tasks | Asking questions |  |  | 0.25 | 0.25 | 0
|  | Max 4 hours tasks | [5 empty] | 0
Look into next presentation date
Resolve potential ehtical requirements
Fill in all ILOs (discuss with team)
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 16.25 | 18.75 | 2.5
Week 13
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-12-02 | Done | Max 4 hours tasks | Meeting about presentation | Meeting |  | 1 | 1.5 | 0.5
2024-12-02 | Done | Max 4 hours tasks | Worklog | Evidencing |  | 1 | 1 | 0
2024-12-02 | Done | Max 4 hours tasks | BRD | Debugging |  | 2 | 2 | 0
2024-12-02 | Done | Max 4 hours tasks | Ocean 3D | Break |  | 1 | 1 | 0
2024-12-02 | Done | Max 4 hours tasks | Looking into frontend | Research |  | 2 | 0.5 | -1.5
2024-12-02 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-03 | Done | Max 4 hours tasks | Frontend | Research |  | 1 | 2 | 1
2024-12-03 | Done | Max 4 hours tasks | Qualitive analysis | Research |  | 2 | 3 | 1
2024-12-03 | Done | Max 4 hours tasks | Teammeating | Meeting |  | 0.5 | 0.5 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-04 | Cancelled | Max 4 hours tasks | meeting |  |  | 0.5 | 0.5 | 0
2024-12-04 | Done | Max 4 hours tasks | feedback |  |  | 0.5 | 0.5 | 0
2024-12-04 | Done | Max 4 hours tasks | lecture |  |  | 3 | 4 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-05 | Done | Max 4 hours tasks | meeting |  |  | 0.5 | 0.5 | 0
2024-12-05 | Done | Max 4 hours tasks | working on retake |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-06 | Done | Max 4 hours tasks | meeting |  |  | 0.5 | 0.5 | 0
2024-12-06 | Done | Max 4 hours tasks | dashboard |  |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 19.5 | 21.5 | 2
Week 14
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-12-09 | Done | Max 4 hours tasks | break |  |  | 1 | 1 | 0
2024-12-09 | Done | Max 4 hours tasks | meeting |  |  | 1 | 1 | 0
2024-12-09 | Done | Max 4 hours tasks | footage for testing |  |  | 2 | 2 | 0
2024-12-09 | Done | Max 4 hours tasks | documentation |  |  | 1 | 2 | 1
2024-12-09 | Done | Max 4 hours tasks | sending out poll for presentation |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-10 | Done | Max 4 hours tasks | worklog |  |  | 2 | 2 | 0
2024-12-10 | Done | Max 4 hours tasks | meeting |  |  | 0.5 | 0.5 | 0
2024-12-10 | Done | Max 4 hours tasks | work on presentation |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-11 | Done | Max 4 hours tasks | meeting |  |  | 0.5 | 0.5 | 0
2024-12-11 | Done | Max 4 hours tasks | Qualitive analysis |  |  | 3 | 4 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-12 | Done | Max 4 hours tasks | sending out invitations |  |  | 1 | 1 | 0
2024-12-12 | Done | Max 4 hours tasks | Break |  |  | 1 | 1 | 0
2024-12-12 | Done | Max 4 hours tasks | meeting |  |  | 1 | 1 | 0
2024-12-12 | Done | Max 4 hours tasks | presentation work |  |  | 2 | 2 | 0
2024-12-12 | Done | Max 4 hours tasks | gathering footage |  |  | 4 | 4 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-13 | Done | Max 4 hours tasks | Meeting |  |  | 0.5 | 0.5 | 0
2024-12-13 | Done | Max 4 hours tasks | editing video for presentation |  |  | 4 | 5 | 1
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 26.5 | 29.5 | 3
Week 15
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-12-16 | Done | Max 4 hours tasks | Presentation |  |  | 1 | 1 | 0
2024-12-16 | Done | Max 4 hours tasks | Prep for presenting |  |  | 3 | 4 | 1
2024-12-16 | Done | Max 4 hours tasks | break |  |  | 1 | 1 | 0
2024-12-16 | Done | Max 4 hours tasks | feedback from presentation |  |  | 1 | 1 | 0
2024-12-16 | Done | Max 4 hours tasks | dashboard |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-17 | Done | Max 4 hours tasks | meeting |  |  | 0.5 | 0.5 | 0
2024-12-17 | Done | Max 4 hours tasks | retake |  |  | 1 | 0 | -1
2024-12-17 | Done | Max 4 hours tasks | worklog |  |  | 2 | 2 | 0
2024-12-17 | Done | Max 4 hours tasks | notes |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-18 | Done | Max 4 hours tasks | meeting |  |  | 0.5 | 0.5 | 0
2024-12-18 | Done | Max 4 hours tasks | learninglog |  |  | 2 | 2 | 0
2024-12-18 | Done | Max 4 hours tasks | send notes to bram |  |  | 1 | 1 | 0
2024-12-18 | Done | Max 4 hours tasks | Peer reviews |  |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-19 | Done | Max 4 hours tasks | Work on retake | Evidencing |  | 2 | 3 | 1
2024-12-19 | Done | Max 4 hours tasks | Start of the report | Evidencing |  | 2 | 2 | 0
2024-12-19 | Done | Max 4 hours tasks | Meeting | Meeting |  | 1 | 1 | 0
2024-12-19 | Done | Max 4 hours tasks | break | Break |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2024-12-20 | Cancelled | Max 4 hours tasks | meeting | Meeting |  | 0.5 | 0.5 | 0
2024-12-20 | Blocked | Max 4 hours tasks | Grafisch Lycuem Setup | Debugging |  | 4 | 6 | 2
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 26.5 | 29.5 | 3
Week 16
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-06 | Done | Max 4 hours tasks | footage for testing | Testing |  | 1 | 3 | 2
2025-01-06 | Done | Max 4 hours tasks | meeting with group | Meeting |  | 1 | 1 | 0
2025-01-06 | Done | Max 4 hours tasks | continue'd work on report | Evidencing |  | 2 | 3 | 1
2025-01-06 | Done | Max 4 hours tasks | break | Break |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-07 | Done | Max 4 hours tasks | Teammeating | Meeting |  | 0.5 | 0.5 | 0
2025-01-07 | Done | Max 4 hours tasks | sending out poll for presentation | Meeting |  | 1 | 1 | 0
2025-01-07 | Done | Max 4 hours tasks | work on presentation | Evidencing |  | 1 | 1 | 0
2025-01-07 | Delayed | Max 4 hours tasks | work on report | Evidencing |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-08 | Done | Max 4 hours tasks | Teammeeting | Meeting |  | 0.5 | 0.5 | 0
2025-01-08 | Done | Max 4 hours tasks | presentation slides | Evidencing |  | 2 | 2 | 0
2025-01-08 | Done | Max 4 hours tasks | Report | Evidencing |  | 1 | 0.5 | -0.5
2025-01-08 | Done | Max 4 hours tasks | learninglog / worklog | Evidencing |  | 2 | 2 | 0
2025-01-08 | Done | Max 4 hours tasks | Trello | Evidencing |  | 0.5 | 0.5 | 0
2025-01-08 | Done | Max 4 hours tasks | Peer reviews in learninglog | Research |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-09 | Done | Max 4 hours tasks | break | Meeting |  | 1 | 1 | 0
2025-01-09 | Done | Max 4 hours tasks | Report | Evidencing |  | 1 | 1 | 0
2025-01-09 | Done | Max 4 hours tasks | presentation | Evidencing |  | 2 | 1 | -1
2025-01-09 | Done | Max 4 hours tasks | scheduling presentation Monday/Thursday | Meeting |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-10 | Done | Max 4 hours tasks | Teammeeting | Meeting |  | 1 | 1 | 0
2025-01-10 | Done | Max 4 hours tasks | presentation slides | Evidencing |  | 1 | 1 | 0
2025-01-10 | Cancelled | Max 4 hours tasks | Report | Evidencing |  | 2 | 0 | -2
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 24.5 | 25 | 0.5
Week 17
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-13 | Done | Max 4 hours tasks | Meeting |  |  | 1 | 1 | 0
2025-01-13 | Done | Max 4 hours tasks | Data collection |  |  | 2 | 3 | 1
2025-01-13 | Done | Max 4 hours tasks | Worklog |  |  | 2 | 1 | -1
2025-01-13 | Done | Max 4 hours tasks | Presentation |  |  | 1 | 3 | 2
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-14 | Done | Max 4 hours tasks | Meeting |  |  | 1 | 0.5 | -0.5
2025-01-14 | Done | Max 4 hours tasks | Sending invitatiions |  |  | 1 | 0.5 | -0.5
2025-01-14 | Done | Max 4 hours tasks | Technicial report |  |  | 1 | 2 | 1
2025-01-14 | Done | Max 4 hours tasks | Presentation |  |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-15 | Done | Max 4 hours tasks | Meeting |  |  | 1 | 1 | 0
2025-01-15 | Done | Max 4 hours tasks | Presentation adjust |  |  | 1 | 2 | 1
2025-01-15 | Done | Max 4 hours tasks | Technicial report |  |  | 2 | 3 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-16 | Done | Max 4 hours tasks | Presentation |  |  | 1 | 1 | 0
2025-01-16 | Done | Max 4 hours tasks | feedback from presentation |  |  | 1 | 1 | 0
2025-01-16 | Done | Max 4 hours tasks | Break |  |  | 1 | 1 | 0
2025-01-16 | Done | Max 4 hours tasks | Meeting |  |  | 0.5 | 0.5 | 0
2025-01-16 | Done | Max 4 hours tasks | ILOs |  |  | 2 | 1 | -1
2025-01-16 | Done | Max 4 hours tasks | Data collection |  |  | 3 | 3 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-17 | Done | Max 4 hours tasks | Meeting |  |  | 0.5 | 0.5 | 0
2025-01-17 | Done | Max 4 hours tasks | Technicial report |  |  | 3 | 5 | 2
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 26 | 32 | 6
Week 18
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-20 | Done | Max 4 hours tasks | Practise presentation | Meeting |  | 2 | 2 | 0
2025-01-20 | Done | Max 4 hours tasks | Break | Break |  | 1 | 1 | 0
2025-01-20 | Done | Max 4 hours tasks | Team meating | Meeting |  | 1 | 0.5 | -0.5
2025-01-20 | Done | Max 4 hours tasks | ILOs | Evidencing |  | 3 | 2 | -1
2025-01-20 | Done | Max 4 hours tasks | Adjust presentation on feedback | Debugging |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-21 | Done | Max 4 hours tasks | Literture review | Research |  | 1 | 1 | 0
2025-01-21 | Done | Max 4 hours tasks | Meeting | Meeting |  | 0.5 | 0.5 | 0
2025-01-21 | Done | Max 4 hours tasks | Adjust presentation on feedback | Debugging |  | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-22 | Done | Max 4 hours tasks | Meeting | Meeting |  | 0.5 | 0.5 | 0
2025-01-22 | Cancelled | Max 4 hours tasks | BRD | Evidencing |  | 1 | 0 | -1
2025-01-22 | Done | Max 4 hours tasks | learninglog / worklog | Evidencing |  | 2 | 1 | -1
2025-01-22 | Done | Max 4 hours tasks | ILOs | Evidencing |  | 1 | 2 | 1
|  | Max 4 hours tasks | [5 empty] | 0
2025-01-23 | Done | Max 4 hours tasks | End presentation | Evidencing |  | 1 | 1 | 0
2025-01-23 | Done | Max 4 hours tasks | Listening to presentation | Meeting |  | 4 | 7 | 3
|  | Max 4 hours tasks | [5 empty] | 0
2024-01-24 | Cancelled | Max 4 hours tasks | Peer reviews | Evidencing |  | 1 | 0 | -1
2024-01-24 | Done | Max 4 hours tasks | Retrospective | Meeting |  | 1 | 1 | 0
2024-01-24 | Done | Max 4 hours tasks | meetings | Meeting |  | 0.5 | 1 | 0.5
2024-01-24 | Done | Max 4 hours tasks | ILOs | Evidencing |  | 2 | 3 | 1
2024-01-24 | Done | Max 4 hours tasks | Technicial report | Evidencing |  | 1 | 0.5 | -0.5
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
End Presentation
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 25.5 | 26 | 0.5
Week 19
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 0 | 0 | 0
Week 20
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 0 | 0 | 0

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
ILO 1 | [8 empty] | 0
ILO 2 | W1: 0 | 0
ILO 3 | [8 empty] | 0
ILO 4 | [8 empty] | 0
ILO 5 | [8 empty] | 0
ILO 6 | [8 empty] | 0
ILO 7 | [8 empty] | 0
ILO 8 | [8 empty] | 0
ILO 9 | [8 empty] | 0
ILO 10 | [8 empty] | 0
ILO 11 | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
Use a formula like this to get your data from Worklog sheet : =IFERROR(SUM(FILTER('Worklog_Tasks&Times'!$H$5:$H$14,'Worklog_Tasks&Times'!$F$5:$F$14=$B4)),0)

## Drop-downs
Task Status | Task Type | ILO selection
- | - | ILO 1
Planned | Design | ILO 2
Unplanned | Meeting | ILO 3
Blocked | Programming | ILO 4
In-Progress | Research | ILO 5
Done | Testing | ILO 6
Delayed | Workshop | ILO 7
Cancelled | Planning | ILO 8
| Evidencing | ILO 9
| Debugging | ILO 10
| Lecture | ILO 11
Study
Unplanned
Distraction
Break